## plan
|  |  | Task Owner | Phase 1 | [7 empty] | Phase 2
|  |  |  | Week 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 1-6 | 1-7 | 1-8 | Week 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 2-6 | 2-7 | 2-8
Task Id | Task Description
1 | Project definition | bar: Phase 1 1-2; Phase 1 1-8
1-1 |  | - confirmation of requirements | TS/ASD | bar: Phase 1 1-2
1-2 |  | - scope definition | All
2 | Data pre-processing
2-1 |  | - initial review & exploration | bar: Phase 1 Week 1-1 to Phase 1 1-5
2-2 |  | - top-level categorisation | bar: Phase 1 1-3 to Phase 1 1-4; Phase 1 1-7
2-3 |  | - cleaning & enrichment | bar: Phase 1 Week 1-1 to Phase 1 1-5; Phase 1 1-7
3 | Detailed exploratory analysis & modeling
3-1 |  | - complete data categorisation - by and within grade type | ASD | bar: Phase 1 1-3 to Phase 1 1-4; Phase 1 1-8
3-2 |  | - document data structure and content, along with key changes in data/awards/reporting | bar: Phase 1 1-2 to Phase 1 1-5
3-3 |  | - define basic statistical calculations, other indicators and metrics to be implemented | ASD | bar: Phase 1 1-3 to Phase 1 1-5; Phase 1 1-7
3-4 |  | - use text analysis to track variation in subjects over time | BB | bar: Phase 1 1-4 to Phase 1 1-7
3-5 |  | - identify (any) additional advanced data modeling | bar: Phase 1 1-7 to Phase 1 1-8
3-6 |  | - initial scenario-based UI design | ASD | bar: Phase 1 1-4 to Phase 1 1-5
3-7 |  | - identify & explore visualisation techniques | All volunteers | bar: Phase 1 1-4 to Phase 1 1-6
4 | Stage 1 reporting
4-1 |  | - statistical and visual analysis and results | ASD | bar: Phase 1 1-5 to Phase 1 1-7
4-2 |  | - evaluation & validation of initial results & design | ASD | bar: Phase 1 1-2 to Phase 1 1-8
5 | Requirements review & final UI design
5-1 |  | - additional data exploration | bar: Phase 1 1-6 to Phase 1 1-8
5-2 |  | - identification of other key end user characteristics | bar: Phase 1 1-6
5-3 |  | - development of storyline | ASD | bar: Phase 1 1-6 to Phase 1 1-7
5-4 |  | - tool exploration | All volunteers | bar: Phase 1 1-5 to Phase 1 1-6
6 | Deployment - Phase 1 Prototype | bar: Phase 1 1-8
6-1 |  | - project review | bar: Phase 1 1-5; Phase 1 1-8
7 | Finalisation of requirements and design
8 | Construction of UI
9 | Construction of visualisations
10 | Development of analytics support
10-1 |  | - analytics functionality
10-2 |  | - reporting functionality
11 | Evaluation
12 | Presentation of results - reporting & exploration
13 | Final evaluation
14 | Deployment
15 | Handover

## plan_ph2
|  |  | Task Owner | Phase 2
|  |  |  | Week 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 2-6 | 2-7 | 2-8
Task Id | Task Description
7 | Finalisation of requirements and design
7-1 |  | - implement feedback from Ph1 review meeting | All volunteers | bar: Phase 2 Week 2-1 to Phase 2 2-2
7-2 |  | - identification of other key end user characteristics | EM | bar: Phase 2 Week 2-1 to Phase 2 2-2
7-3 |  | - confirmation of requirements | TS/ASD | bar: Phase 2 2-2; Phase 2 2-5
7-4 |  | - scope definition | All | bar: Phase 2 Week 2-1 to Phase 2 2-2
8 | Data Extraction - HNCs & HNDS; teacher data, etc.
8-1 |  | - extract from Excel sheets | All volunteers | bar: Phase 2 Week 2-1 to Phase 2 2-4
8-2 |  | - run error checking and load into DB | All volunteers | bar: Phase 2 Week 2-1 to Phase 2 2-4
8-3 |  | - update data structure and flow diagram | All volunteers | bar: Phase 2 Week 2-1 to Phase 2 2-3
9 | Detailed exploratory analysis & modeling
9-1 |  | - document key changes in data/awards/reporting | SQA/Toni | bar: Phase 2 2-5
9-2 |  | - define additional indicators and metrics to be implemented | All | bar: Phase 2 2-3; Phase 2 2-6
9-3 |  | - additional data exploration | All | bar: Phase 2 2-2 to Phase 2 2-8
9-4 |  | - use text analysis to create subject groups | BB | bar: Phase 2 2-2 to Phase 2 2-5; Phase 2 2-8
9-5 |  | - analysis of grades and grade boundaries | BB | bar: Phase 2 2-2 to Phase 2 2-5; Phase 2 2-8
10 | Requirements review & Construction of UI
10-1 |  | - update to scenario-based UI design & storyline | EM/BB/ASD | bar: Phase 2 2-2 to Phase 2 2-3; Phase 2 2-6
10-2 |  | - finalisation of visualisation techniques | EM/AK | bar: Phase 2 2-2 to Phase 2 2-4; Phase 2 2-7
10-3 |  | - cross-platform compatibility & visual impairments (key - colour-blindness) | EM | bar: Phase 2 2-2; Phase 2 2-5; Phase 2 2-7
10-4 |  | - functionality for download - data subsets and charts | ASD | bar: Phase 2 2-6 to Phase 2 2-7
10-5 |  | - confirmation of UI for MVP / first working prototype | TS/All | bar: Phase 2 2-5 to Phase 2 2-6
11 | Stage 2 reporting
11-1 |  | - statistical and visual analysis and results | ASD | bar: Phase 2 2-5 to Phase 2 2-7
11-2 |  | - evaluation & validation of initial results & design | ASD | bar: Phase 2 2-2 to Phase 2 2-8
12 | Evaluation
12-1 |  | - internal system testing | All | bar: Phase 2 2-7 to Phase 2 2-8
12-2 |  | - usability evaluation | All | bar: Phase 2 2-7 to Phase 2 2-8
13 | Deployment - 1st working Prototype
13-1 |  | - project review | All volunteers | bar: Phase 2 2-5; Phase 2 2-8
13-2 |  | - delivery of MVP | bar: Phase 2 2-8
PH3
14 | Presentation of results - reporting & exploration
15 | Final evaluation
16 | Deployment
17 | Handover
Week 2-1 - 3rd Jan
Working site deployed publicly 7th Mar

## deliverables
No. | Due | Deliverables
1 | S1-W | Data store & documentation - incl. errors, assumptions and key changes to awards
2 |  | Map of requirements to metrics
3 |  | Initial results & insight gained
4 |  | UI design & user scenarios
5 | S1-W8 | Deployment v1 - mainly static visualisation & reporting
6 | S2-W | Deployment v2 - interactive, web-based visualisation

## task_owners
Initials | Name | Hours/Wk | Notes
TS | Toni Scullion | N/A
ASD | Aba-Sah Dadzie | 12 | hours may go down to 8
MS | Matthew Shedden | 6
MP | Marta Pasikowska |  | Code Clan grad mentee
BB | Blaga Baycheva | 6 | may go up to 10
EM | Eleanor Mitchell
AK | Ali Kanji